## Lab 1 Time Tracking
Student Name: | John Smith
Date | Start Time | Ending Time | Interruption Time | Delta (Minutes) | Planning | Design | Implementation | Review | Compilation | Testing | Post-Mortem
[5 empty] | 55 | 50 | 48 | 47 | 45 | 44 | 6
2009-01-01 | 12:00 | 13:00 | 0:05 | 55 | 1
2009-01-01 | 13:00 | 14:00 | 0:10 | 50 |  | 1
2009-01-01 | 14:00 | 15:00 | 0:12 | 48 |  |  | 1
2009-01-01 | 15:00 | 16:00 | 0:13 | 47 |  |  |  | 1
2009-01-01 | 16:00 | 17:00 | 0:15 | 45 |  |  |  |  | 1
2009-01-01 | 18:00 | 19:00 | 0:16 | 44 | [5 empty] | 1
2009-01-01 | 19:00 | 19:10 | 0:04 | 6 | [6 empty] | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Lab 1 Record
Student Name: | John Smith
Lab 1 Record
Phase | Time Spent | % of Time | Defects Removed | % removed
Planning | 55 | 18.64% |  | 0%
Design | 50 | 16.95% | 0 | 0%
Coding | 48 | 16.27% |  | 0%
Code Review | 47 | 15.93% |  | 0%
Compile | 45 | 15.25% | 3 | 50%
Test | 44 | 14.92% | 2 | 33.33%
Postmortem | 6 | 2.034% | 1 | 16.67%
Totals | 295 | 100% | 6 | 100%
Total NCLOC | 78
# of Methods | 25
NCLOC/Method | 3.12
Development Rate | 15.8644 | LOC/Hour
Only non-gray cells can be changed.

## Lab 2 Estimation
Student Name: | John Smith
Lab 2 Estimation
Number of Methods
Class Name | Small | Medium | Large | LOC Count
bob.java | 1 | 2 | 3 | 26.52
bill.java | 5 | 6 | 1 | 32.76
0
0
0
0
0
0
0
Total | 6 | 8 | 4 | 59.28
Estimated Effort (Minutes) | 224.2
Estimated Effort (Hours) | 3.7367
Directions
Start by recording an estimate of the number of estimated methods.
Only non-gray cells can be changed.

## Lab 2 Workplan
Student Name: | John Smith
Lab 2 Workplan
Required Via Estimate |  |  | 41.8 | 38 | 36.48 | 35.72 | 34.2 | 33.44 | 4.56
Scheduled |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Error |  |  | 41.8 | 38 | 36.48 | 35.72 | 34.2 | 33.44 | 4.56
Date | Time to spend on activity | Delta (Minutes) | Planning | Design | Implementation | Review | Compilation | Testing | Post-Mortem
2009-01-01 | 0:13 | 13
2009-01-01 | 0:15 | 15
2009-01-01 | 0:16 | 16
2009-01-01 | 0:04 | 4
2009-01-01 | 0:15 | 15
2009-01-01 | 0:16 | 16
2009-01-01 | 0:04 | 4
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Lab 2 Time Tracking
Student Name: | John Smith
Lab 2 Time Tracking
Date | Start Time | Ending Time | Interruption Time | Delta (Minutes) | Planning | Design | Implementation | Review | Compilation | Testing | Post-Mortem
[5 empty] | 47 | 45 | 44 | 56 | 45 | 44 | 6
2009-01-01 | 12:00 | 13:00 | 0:13 | 47 | 1
2009-01-01 | 13:00 | 14:00 | 0:15 | 45 |  | 1
2009-01-01 | 14:00 | 15:00 | 0:16 | 44 |  |  | 1
2009-01-01 | 15:00 | 16:00 | 0:04 | 56 |  |  |  | 1
2009-01-01 | 16:00 | 17:00 | 0:15 | 45 |  |  |  |  | 1
2009-01-01 | 18:00 | 19:00 | 0:16 | 44 | [5 empty] | 1
2009-01-01 | 19:00 | 19:10 | 0:04 | 6 | [6 empty] | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Lab 2 Record
Student Name: | John Smith
Lab 2 Record
| Time Spent |  |  | Defects Removed
Phase | Actual | Estimated | % Error | Actual | Estimated | % Error
Planning | 47 | 41.8 | -12.44% | 0 | 0
Design | 45 | 38 | -18.42% | 0 | 0
Coding | 44 | 36.48 | -20.61% | 0 | 0
Code Review | 56 | 35.72 | -56.77% | 5 | 0
Compile | 45 | 34.2 | -31.58% | 3 | 2.28 | -31.58%
Test | 44 | 33.44 | -31.58% | 8 | 1.52 | -426.3%
Postmortem | 6 | 4.56 | -31.58% | 1 | 0.76 | -31.58%
Totals | 287 | 224.2 | -28.01% | 17 | 4.56
| Actual | Estimated | % Error
Total NCLOC | 205 | 59.28 | -245.8%
# of Methods | 25 | 18 | -38.89%
NCLOC/Method | 8.2 | 3.12 | -162.8%
Development Rate | 42.8571 | 15.8644 | -170.1%
Directions
Record all elapsed times, less interruptions, in minutes.
Only non-gray cells can be changed.
Positive errors are over-estimates and negative errors are under estimates.